## PAY APP
|  |  | MODIFIED PAY APPLICATION |  |  |  | **Due on 25th of each month
| PAY APPLICATION NUMBER: | 1 |  |  | FOR PAY PERIOD ENDING:
| JOB NAME: | Hampton Manor of Hamburg
| TO CONTRACTOR: | BCG Construction, Inc. |  |  | FROM SUB-CONTRACTOR: |  | (Company name)
|  | 224 E Larkin Street |  |  |  |  | (address 1)
|  | Midland, MI 48640 |  |  |  |  | (address 2)
|  |  | CONTRACT VALUES | ALL PRIOR INVOICES | THIS INVOICE | TOTAL INVOICED | PERCENT COMPLETED | REMAINING BALANCE
SCHEDULE OF VALUES:
| PLUMBING UNDERGROUND |  | 5000 |  | 1200 | 1200 | 24% | 3800
| PLUMBING ROUGH-IN |  | 15000 |  |  | 0 | 0% | 15000
| PLUMBING FINISH |  | 10000 |  |  | 0 | 0% | 10000
1 | ORIGINAL CONTRACT SUM |  | 30000 | 0 | 1200 | 1200 | 4% | 28800
CHANGE ORDERS, if any:
2 | TOTAL APPROVED CHANGE ORDERS |  | 0 | 0 | 0 | 0 | 0% | 0
| REVISED CONTRACT SUM (1+ 2) |  | 30000 | 0 | 1200 | 1200 | 4% | 28800
ONLY update yellow shaded fields

## BLANK PAY APP TO MANUALLY ENTER
|  |  | MODIFIED PAY APPLICATION |  |  |  | **Due on 25th of each month
| PAY APPLICATION NUMBER: |  |  |  | FOR PAY PERIOD ENDING:
JOB NAME:
| TO CONTRACTOR: | BCG Construction, Inc. |  |  | FROM SUB-CONTRACTOR:
224 E Larkin Street
Midland, MI 48640
|  |  | CONTRACT VALUES | ALL PRIOR INVOICES | THIS INVOICE | TOTAL INVOICED | PERCENT COMPLETED | REMAINING BALANCE
SCHEDULE OF VALUES:
1 | ORIGINAL CONTRACT SUM
CHANGE ORDERS, if any:
2 | TOTAL APPROVED CHANGE ORDERS
REVISED CONTRACT SUM (1+ 2)
ONLY update yellow shaded fields